## Sheet1
No | Task Name | Duration | Week 1 | [6 empty] | Week 2
|  |  | S | S | R | K | J | S | M | S | S | R | K | J | S | M
1 | CMS | 5 days
1.1 | Design database | bar: Week 1 S
1.2 | Develop API | bar: Week 1 S
1.3 | CRUD product | bar: Week 1 S
1.4 | CRUD category product | bar: Week 1 R
1.5 | Test & debug | bar: Week 1 K
1.6 | Resolving | bar: Week 2 M
2 | Landing page | 3 days
2.1 | Navigation | bar: Week 1 J
2.2 | Carousel | bar: Week 1 J
2.3 | List Category | bar: Week 1 S
2.4 | New product | bar: Week 1 S
2.5 | Hot Promo | bar: Week 1 S
2.6 | All product | bar: Week 1 M
2.7 | Footer component | bar: Week 1 M
3 | Category page | 2 days
3.1 | Glance | bar: Week 2 S
3.2 | List Category | bar: Week 2 S
4 | Our product | 2 days
4.1 | Filter product | bar: Week 2 R
4.2 | Item product | bar: Week 2 K
5 | Detail Product | 2 days
5.1 | Breadcumbs | bar: Week 2 J
5.2 | Description product | bar: Week 2 J
5.3 | Link to Shopee & Tokped | bar: Week 2 S
Note :
1. Mulai pengerjaan setelah ada pembayaran 50% DP